## plan_20260308_1531
Academic Skills Practice App
Module / Content | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Person in Charge
Main Tasks | Find materials + set up framework | Basically complete and lightweight core functions | Add details to lightweight design | Overall performance optimization, fix known bugs | Iterate based on internal test feedback, final pre-launch check | All
Database | Design + deploy for use | Refine database based on user and actual changing needs | Refine database based on user and actual changing needs, optimize query performance | Refine database based on user and actual changing needs, data backup and disaster recovery | Refine database based on user and actual changing needs, security hardening (prevent SQL injection, etc.) | Xingzhuo Bao
Personal Center | Complete login/registration code | Connect to existing database + refine UI | Add friend social features (including follower count, friends list, etc.) | Add favorites function, add personal vocabulary stats and other details | Improve password encryption, ensure no backdoors, deliver product | Sihan Wang
Vocabulary Function | Vocabulary book materials | Import materials into database, implement vocabulary book memorization | Support word bookmarking, mark familiar/new words, etc. | Support personal custom vocabulary books for memorization and check-in to provide emotional value | Import word audio, refine word example sentences and other details | Jing Lu
Knowledge Cards | Trivia materials | Input knowledge materials, implement like and popularity sorting | Refine card UI for better usability | Add card categorization and tagging | Card sharing function, support sharing to community | Yukun Wang
Community Function | Community template | Implement complete community environment (post CRUD, like, comment) | User forum level and points system | Community reporting and moderation mechanism | Community topic square, optimize hot recommendation algorithm | Jiachi Zhu
Listening | TED listening clips | Adjustable listening speed | Filter listening materials by level | Support intensive listening — refine to sentence-by-sentence playback | Listening check-in, study plan | Qiyin Huang
Writing | Academic paper excerpt materials | Support bookmarking and highlighting key sentences in academic papers | Writing template library, support different genres | Writing check-in, peer review function | AI writing assistance, grammar check and polishing suggestions | Hang Ge
Agile support | Assist in database architecture setup; Establish coding standards | Manage cross-module API integration; pair program with members facing technical blockers | Lead technical spikes for complex logic | Address technical debt and optimize end-to-end user flows | Manage the deployment pipeline and perform final security & stress audits before launch | Yihan Wang