DIICSU Academic Transition Hub - Agile Development Plan

1. Product Goal & Vision

Product Goal Statement:
To build a comprehensive web platform that helps DIICSU incoming students transition from local education to an English-Medium Instruction (EMI) environment. The site aims to reduce academic anxiety by providing guidance on university tools, academic integrity, and interactive skill practice (listening, speaking, and vocabulary) before the semester begins.

Target Users:
Incoming DIICSU undergraduate students who are non-native English speakers and feel anxious about participating in a 100% English-taught academic environment.

2. Team Structure & Role Rotation

To demonstrate a leaderless, self-organizing team, the roles of Product Owner (PO) and Scrum Master (SM) rotate each Sprint.

| Sprint | Week | Product Owner (PO) | Scrum Master (SM) | Development Team |
| --- | --- | --- | --- | --- |
| 1 | 3 | Jing Lu | Qiyin Huang | All other members |
| 2 | 4 | Sihan Wang | Yihan Wang | All other members |
| 3 | 5 | Hang Ge | Yukun Wang | All other members |
| 4 | 6 | Jiachi Zhu | Xingzhuo Bao | All other members |

3. Team Member Responsibility Matrix

Workload is distributed based on core modules. Yihan Wang manages the technical "glue" (database maintenance/Code repository management and testing) to facilitate the self-organizing structure.

| Member | Core Responsibility | Key Deliverables |
| --- | --- | --- |
| Sihan Wang | Dashboard & Guidance | Teams tutorial, Intro cards, Academic misconduct guide. |
| Qiyin Huang | Listening Practice | Lecture audio player, comprehension quiz logic. |
| Jing Lu | Listening Practice | Listening content curation, difficulty leveling. |
| Hang Ge | Speaking Practice | "Speak to Teacher" simulation, voice recording UI. |
| Xingzhuo Bao | Speaking Practice | "Group Discussion" scenarios, speaking feedback UI. |
| Jiachi Zhu | Interaction | Forum module, AI Assistant AP. |
| Yukun Wang | Vocabulary & UI | Flashcards system, site-wide CSS/Design system. |
| Yihan Wang | Coordination & Backend | Database schema, Integration. |

4. Product Backlog (Ordered by Value)

| Rank | ID | User Story | Priority | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1 | US01 | As a new English learner(DIICSU), I want to see a dashboard of "How-to" cards so I can learn to use Teams and DIICSU tools. | MUST-DO | 5 | Cards for Teams, Misconduct, and Intro are interactive and readable. |
| 2 | US02 | As a new English learner(DIICSU), I want to listen to sample lecture clips so I can get used to academic accents. | MUST-DO | 8 | Audio player works; includes "Check for Understanding" questions. |
| 3 | US03 | As a new English learner(DIICSU), I want to learn academic vocabulary so I can prepare for lectures. | MUST-DO | 5 | Flip animation for cards; ability to mark words as "Learned". |
| 4 | US04 | As a new English learner(DIICSU), I want to simulate a conversation. | MUST-DO | 8 | Voice recording works; visual prompts for dialogue provided. |
| 5 | US05 | As a new English learner(DIICSU), I want to post questions in a forum so I can interact with my future peers. | SHOULD-DO | 8 | Users can create threads, reply, and view topics by category. |
| 6 | US06 | As a new English learner(DIICSU), I want an AI assistant to roleplay as a classmate so I can practice speaking anytime. | SHOULD-DO | 13 | Integration with AI API; real-time text/voice responses for Speaking. |
| 7 | US07 | As a new English learner(DIICSU), I want to see my progress in each skill so I feel more confident about my preparation. | SHOULD-DO | 5 | Visual progress bars/stats on the user dashboard. |
| 8 | US08 | As a new English learner(DIICSU), I want to receive AI feedback on my speaking so I can correct my grammar/fluency. | COULD-DO | 8 | AI provides a summary report after a speaking session. |

5. Sprint Plans

Sprint 0 (Week 2): Preparation & Design

- Tasks: Define Tech Stack (flask), Design prototype, set up GitHub repository, Sets up the Database.

- Output: Architecture Diagram, UI prototype.

- Expected Risks: Potential code merge conflicts due to unfamiliarity with GitHub collaboration; inadequate initial database schema design may force frequent, time-consuming structural modifications later.

- Review: Wait for filling in

Sprint 1 (Week 3): Foundation & Knowledge Base

- Sprint Goal: Deliver the Dashboard guidance and Vocabulary.

- Key Tasks: Develop US01 (Guidance Cards) and US03 (Flashcards).

- Output: Functional landing page with educational content.

- Expected Risks: Data entry for educational content may take longer than scheduled; the front-end UI layout might break during responsive adaptation across different device screens.

- Review: Wait for filling in

Sprint 2 (Week 4): Optimize performance and function expansion

- Sprint Goal: Optimize database performance and add functions for listening and speaking practice

- Key Tasks: Qiyin/Jing finish Listening player; Hang/Xingzhuo finish Speaking UI and recording functionality.

- Output: The all of practices function is work.

- Expected Risks: Database performance optimization might inadvertently cause regressions or break existing queries.

- Review: Wait for filling in

Sprint 3 (Week 5): Interaction & AI Integration

- Sprint Goal: Make adjustments based on clients feedback

- Key Tasks: Jiachi deploys the Forum and integrates AI API for US06 (AI Assistant).

- Output: Interactive community features and AI-simulated dialogue.

- Expected Risks: Addressing client feedback might lead to scope creep, delaying the Forum and AI tasks; the third-party AI API could experience high latency or rate limit restrictions; potential data synchronization bugs in the forum during concurrent user posts.

- Review: Wait for filling in

Sprint 4 (Week 6): Integration, Testing & Polishing

- Sprint Goal: Test, debug and deploy

- Key Tasks: Final UI polish by Yukun; stress testing by Yihan; Documentation by the team.

- Output: Production-ready DIICSU Transition Website.

- Expected Risks: Stress testing may expose severe system performance bottlenecks that are difficult to patch in just one week; discrepancies between the local development environment and the final production server could cause unexpected deployment crashes.

- Review: Wait for filling in

6. Definition of Done (DoD)

- Code Quality: All code is reviewed by at least one other team member.

- Testing: Unit tests pass for core logic.

- Usability: UI is responsive (works on mobile and desktop).

- Acceptance: The PO for the specific Sprint signs off on the features against the User Story.

7. Agile Ceremonies

- Daily Standup (15 min): Held on Discord/Teams to discuss progress and blockers.

- Sprint Review: End of each week; demo of the working module to the whole group.

- Sprint Retrospective: Discussion on "What went well" and "How to improve" for the next rotation.